## Activities
Task ID | Activity | Phase | Milestone | Status | Owner | Start | Baseline Finish | Planned Finish | Progress | Predecessor | Last Updated
MIG-1 | Source system profiling | Requirement | Discovery | Done | Pham Hong D | 2026-08-05 | 2026-08-15 | 2026-08-15 | 100 |  | 2026-09-10
MIG-2 | Mapping specification | Design | Discovery | Done | Hoach Bach | 2026-08-15 | 2026-08-25 | 2026-08-25 | 100 | MIG-1 | 2026-09-10
MIG-3 | Extract pipeline | Development | Build | Done | Pham Hong D | 2026-08-25 | 2026-09-04 | 2026-09-04 | 100 | MIG-2 | 2026-09-10
MIG-4 | Transform rules | Development | Build | In Progress | Hoach Bach | 2026-09-04 | 2026-09-14 | 2026-09-14 | 40 | MIG-3 | 2026-09-10
MIG-5 | Dry-run load | Testing | Rehearsal | Not started | Pham Hong D | 2026-09-16 | 2026-09-24 | 2026-09-24 | 0 | MIG-4 | 2026-09-10
MIG-6 | Cutover rehearsal | Testing | Rehearsal | Not started | Hoach Bach | 2026-09-26 | 2026-10-04 | 2026-10-04 | 0 | MIG-5 | 2026-09-10