## Worklog
Task ID | Summary | Status | Blocked | Owner | Estimate | Hours | Date
MIG-Q1 | Null handling in legacy address rows | Closed | No | Pham Hong D | 6 | 14 | 2026-08-21
MIG-Q2 | Duplicate customer keys | Closed | No | Hoach Bach | 8 | 19 | 2026-08-23
MIG-Q3 | Timezone drift on created dates | Open | No | Pham Hong D | 4 | 12 | 2026-08-27
MIG-Q4 | Charset on legacy notes | Open | No | Hoach Bach | 5 | 16 | 2026-08-29