## Sheet1
Payments Core - all issues
Displaying 8 issues at 12/Sep/26 9:00 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Created | Updated | Due Date | Start date | Original Estimate | Time Spent | Progress | Sub-Tasks | Linked Issues | Linked Issues | Parent Link | Product
PAY | PAY-1 | Requirements sign-off | Requirement | Resolved |  | Fixed | Nguyen Van A | Nguyen Van A | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-13 09:00 | 2026-08-03 09:00 | 12 | 14 | 100 |  |  |  |  | Foundations [PAY-EPIC]
PAY | PAY-2 | Ledger schema design | Design | Resolved |  | Fixed | Le Van C | Le Van C | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-27 09:00 | 2026-08-13 09:00 | 8 | 11 | 100 |  | is blocked by PAY-1 |  |  | Foundations [PAY-EPIC]
PAY | PAY-3 | Settlement engine | Development | In Progress |  | Unresolved | Tran Quoc B | Tran Quoc B | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-16 09:00 | 2026-08-27 09:00 | 6 | 9 | 55 |  | is blocked by PAY-2 |  |  | Core build [PAY-EPIC]
PAY | PAY-4 | Reconciliation service | Development | In Progress |  | Unresolved | Nguyen Van A | Nguyen Van A | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-22 09:00 | 2026-09-04 09:00 | 3 | 1 | 30 |  | is blocked by PAY-3 |  |  | Core build [PAY-EPIC]
PAY | PAY-5 | Fraud rules integration | Development | To Do |  | Unresolved | Le Van C | Le Van C | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-18 09:00 | 2026-09-12 09:00 | 4 | 4 | 0 |  | is blocked by PAY-4 |  |  | Core build [PAY-EPIC]
PAY | PAY-6 | Payment gateway cutover | Deployment | To Do |  | Unresolved | Tran Quoc B | Tran Quoc B | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-28 09:00 | 2026-09-20 09:00 | 10 | 10 | 0 |  | is blocked by PAY-5 |  |  | Go-live [PAY-EPIC]
PAY | PAY-7 | Production smoke tests | Testing | To Do |  | Unresolved | My Nguyen | My Nguyen | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-30 09:00 | 2026-09-26 09:00 |  |  | 0 |  | is blocked by PAY-6 |  |  | Go-live [PAY-EPIC]
PAY | PAY-8 | Regulator evidence pack | Requirement | To Do |  | Unresolved | Pham Hong D | Pham Hong D | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-10-02 09:00 | 2026-09-22 09:00 |  |  | 0 |  | is blocked by PAY-4 |  |  | Go-live [PAY-EPIC]