## Sheet1
Customer Portal - all issues
Displaying 7 issues at 12/Sep/26 9:00 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Created | Updated | Due Date | Start date | Original Estimate | Time Spent | Progress | Sub-Tasks | Linked Issues | Linked Issues | Parent Link | Product
POR | POR-1 | Portal UX sign-off | Design | Resolved |  | Fixed | My Nguyen | My Nguyen | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-17 09:00 | 2026-08-08 09:00 | 5 | 8 | 100 |  |  |  |  | Foundations [POR-EPIC]
POR | POR-2 | Account service API | Development | Resolved |  | Fixed | Le Van C | Le Van C | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-29 09:00 | 2026-08-17 09:00 | 4 | 7 | 100 |  | is blocked by POR-1 |  |  | Foundations [POR-EPIC]
POR | POR-3 | Statements screen | Development | In Progress |  | Unresolved | My Nguyen | My Nguyen | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-14 09:00 | 2026-08-29 09:00 | 2 | 0 | 60 |  | is blocked by POR-2 |  |  | Portal build [POR-EPIC]
POR | POR-4 | Payment history integration | Development | To Do |  | Unresolved | Le Van C | Le Van C | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-24 09:00 | 2026-09-10 09:00 | 3 | 1 | 0 |  | is blocked by POR-3 |  |  | Portal build [POR-EPIC]
POR | POR-5 | Accessibility audit | Testing | To Do |  | Unresolved | Pham Hong D | Pham Hong D | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-24 09:00 | 2026-09-18 09:00 | 3 | 3 | 0 |  | is blocked by POR-3 |  |  | Portal build [POR-EPIC]
POR | POR-6 | Customer UAT | Testing | To Do |  | Unresolved | My Nguyen | My Nguyen | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-10-04 09:00 | 2026-09-24 09:00 | 6 | 6 | 0 |  | is blocked by POR-4 |  |  | Release [POR-EPIC]
POR | POR-7 | Portal release | Deployment | To Do |  | Unresolved | Tran Quoc B | Tran Quoc B | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-10-06 09:00 | 2026-10-02 09:00 |  |  | 0 |  | is blocked by POR-6 |  |  | Release [POR-EPIC]