## Activities
Task ID | Activity | Phase | Milestone | Status | Owner | Start | Baseline Finish | Planned Finish | Progress | Predecessor | Last Updated
PAY-1 | Requirements sign-off | Requirement | Foundations | Done | Nguyen Van A | 2026-08-03 | 2026-08-13 | 2026-08-13 | 100 |  | 2026-09-10
PAY-2 | Ledger schema design | Design | Foundations | Done | Le Van C | 2026-08-13 | 2026-08-23 | 2026-08-27 | 100 | PAY-1 | 2026-09-10
PAY-3 | Settlement engine | Development | Core build | In Progress | Tran Quoc B | 2026-08-27 | 2026-08-31 | 2026-09-16 | 55 | PAY-2 | 2026-09-10
PAY-4 | Reconciliation service | Development | Core build | In Progress | Nguyen Van A | 2026-09-04 | 2026-09-08 | 2026-09-22 | 30 | PAY-3 | 2026-09-10
PAY-5 | Fraud rules integration | Development | Core build | Not started | Le Van C | 2026-09-12 | 2026-09-18 | 2026-09-18 | 0 | PAY-4 | 2026-09-10
PAY-6 | Payment gateway cutover | Deployment | Go-live | Not started | Tran Quoc B | 2026-09-20 | 2026-09-28 | 2026-09-28 | 0 | PAY-5 | 2026-09-10
PAY-7 | Production smoke tests | Testing | Go-live | Not started | My Nguyen | 2026-09-26 | 2026-09-30 | 2026-09-30 | 0 | PAY-6 | 2026-09-10
PAY-8 | Regulator evidence pack | Requirement | Go-live | Not started | Pham Hong D | 2026-09-22 | 2026-10-02 | 2026-10-02 | 0 | PAY-4 | 2026-09-10