## Worklog
Task ID | Summary | Status | Blocked | Owner | Estimate | Hours | Date
PAY-Q1 | Rounding on multi-currency settlement | Open | Yes | Tran Quoc B | 12 | 14 | 2026-08-25
PAY-Q2 | Ledger reconciliation mismatch | Open | Yes | Nguyen Van A | 8 | 11 | 2026-08-28
PAY-Q3 | Retry storm under gateway timeout | Open | Yes | Tran Quoc B | 6 | 9 | 2026-09-01
PAY-Q4 | Fee schedule confirmation | Open | Customer | Pham Hong D | 3 | 1 | 2026-09-03
PAY-Q5 | Audit log retention window | Open | No | Le Van C | 4 | 4 | 2026-09-06
PAY-Q6 | Settlement batch performance | Closed | No | Tran Quoc B | 10 | 10 | 2026-08-23