## Activities
Task ID | Activity | Phase | Milestone | Status | Owner | Start | Baseline Finish | Planned Finish | Progress | Predecessor | Last Updated
POR-1 | Portal UX sign-off | Design | Foundations | Done | My Nguyen | 2026-08-08 | 2026-08-17 | 2026-08-17 | 100 |  | 2026-09-10
POR-2 | Account service API | Development | Foundations | Done | Le Van C | 2026-08-17 | 2026-08-27 | 2026-08-29 | 100 | POR-1 | 2026-09-10
POR-3 | Statements screen | Development | Portal build | In Progress | My Nguyen | 2026-08-29 | 2026-09-06 | 2026-09-14 | 60 | POR-2 | 2026-09-10
POR-4 | Payment history integration | Development | Portal build | Not started | Le Van C | 2026-09-10 | 2026-09-16 | 2026-09-24 | 0 | POR-3 | 2026-09-10
POR-5 | Accessibility audit | Testing | Portal build | Not started | Pham Hong D | 2026-09-18 | 2026-09-24 | 2026-09-24 | 0 | POR-3 | 2026-09-10
POR-6 | Customer UAT | Testing | Release | Not started | My Nguyen | 2026-09-24 | 2026-09-30 | 2026-10-04 | 0 | POR-4 | 2026-09-10
POR-7 | Portal release | Deployment | Release | Not started | Tran Quoc B | 2026-10-02 | 2026-10-06 | 2026-10-06 | 0 | POR-6 | 2026-09-10