## Worklog
Task ID | Summary | Status | Blocked | Owner | Estimate | Hours | Date
POR-Q1 | Statement PDF layout on mobile | Open | Yes | My Nguyen | 5 | 8 | 2026-08-31
POR-Q2 | Session timeout on slow networks | Open | Yes | Le Van C | 4 | 7 | 2026-09-02
POR-Q3 | Which balances are shown pre-settlement | Open | Customer | Pham Hong D | 2 | 0 | 2026-08-29
POR-Q4 | Contrast ratio on the statements table | Open | Customer | My Nguyen | 3 | 1 | 2026-08-30
POR-Q5 | Locale formatting for amounts | Open | No | Le Van C | 3 | 3 | 2026-09-07
POR-Q6 | Login redirect loop | Closed | No | Tran Quoc B | 6 | 6 | 2026-08-24