## Sheet1
Data Migration - all issues
Displaying 6 issues at 12/Sep/26 9:00 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Created | Updated | Due Date | Start date | Original Estimate | Time Spent | Progress | Sub-Tasks | Linked Issues | Linked Issues | Parent Link | Product
MIG | MIG-1 | Source system profiling | Requirement | Resolved |  | Fixed | Pham Hong D | Pham Hong D | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-15 09:00 | 2026-08-05 09:00 | 6 | 14 | 100 |  |  |  |  | Discovery [MIG-EPIC]
MIG | MIG-2 | Mapping specification | Design | Resolved |  | Fixed | Hoach Bach | Hoach Bach | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-08-25 09:00 | 2026-08-15 09:00 | 8 | 19 | 100 |  | is blocked by MIG-1 |  |  | Discovery [MIG-EPIC]
MIG | MIG-3 | Extract pipeline | Development | Resolved |  | Fixed | Pham Hong D | Pham Hong D | 2026-07-29 09:00 | 2026-09-10 09:00 | 2026-09-04 09:00 | 2026-08-25 09:00 | 4 | 12 | 100 |  | is blocked by MIG-2 |  |  | Build [MIG-EPIC]
MIG | MIG-4 | Transform rules | Development | In Progress |  | Unresolved | Hoach Bach | Hoach Bach | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-14 09:00 | 2026-09-04 09:00 | 5 | 16 | 40 |  | is blocked by MIG-3 |  |  | Build [MIG-EPIC]
MIG | MIG-5 | Dry-run load | Testing | To Do |  | Unresolved | Pham Hong D | Pham Hong D | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-09-24 09:00 | 2026-09-16 09:00 |  |  | 0 |  | is blocked by MIG-4 |  |  | Rehearsal [MIG-EPIC]
MIG | MIG-6 | Cutover rehearsal | Testing | To Do |  | Unresolved | Hoach Bach | Hoach Bach | 2026-07-29 09:00 | 2026-08-31 09:00 | 2026-10-04 09:00 | 2026-09-26 09:00 |  |  | 0 |  | is blocked by MIG-5 |  |  | Rehearsal [MIG-EPIC]